Educational Scoping Project Plan

Project Dates: Monday 15th June 2026 – Friday 7th August 2026

Project Overview

The Bradford Police Museum is undertaking an 8-week Educational Scoping Project to develop a sustainable, research-informed learning programme that responds to audience need and supports long-term organisational growth. As a volunteer-led museum with increasing demand for educational activity, the current offer has developed organically and now requires a more structured, scalable approach. This project will engage a freelance education specialist to undertake research, consultation, and testing to assess current provision, understand audience needs, and explore effective delivery models. One school visit will be delivered as part of the project to test and evaluate workshop delivery in a live setting. This session will be provided free of charge to support participation and ensure meaningful feedback. The outcome will be a clear, costed, and deliverable education framework that strengthens programme design, supports improved volunteer involvement, and embeds a more strategic and sustainable approach to learning and engagement.

The project is a critical step towards the development of the museum’s ‘Heritage Connections’ programme and a future funding application to the National Lottery Heritage Fund. By working with a specialist, the museum will ensure that this future programme is grounded in sector best practice, shaped by local need, and realistic within its capacity. In the longer term, this will support the introduction of a dedicated education role, strengthen income generation through educational visits, and enable the museum to expand access through inclusive and flexible provision, including in-school, digital, and family learning opportunities. Overall, the project will position the museum to deliver a high-quality, sustainable education offer that is relevant, accessible, and responsive to the communities it serves.

Project Aim

To produce a tested, costed and scalable educational programme model that can be delivered within current capacity and used to support a strong funding application for the development of a larger educational programme.

Project Phases

Phase 1: Discovery & Research

Weeks 1 & 2 - Monday 15th June to Friday 26th June

Activities:

- Review existing educational activity and materials

- Rapid stakeholder consultation:

  - Schools

  - Teachers

  - Partners

- Work to identify:

  - Demand

  - Barriers

  - Gaps

Deliverables:

- Audience Needs Summary

- Barriers & Access Analysis

- Programme Review (what works / what doesn’t)

Phase 2: Testing & Development

Weeks 3 & 4 – Monday 29th June to Friday 10th July

Activities:

- Test adapted workshop formats

- Trial with current volunteer model

- Gather structured feedback

- Conduct volunteer training needs analysis

Deliverables:

- Tested Workshop Models

- Delivery Requirements (staff/volunteers/time)

- Evaluation Summary

Phase 3: Programme Design

Weeks 5 & 6 – Monday 13th July to Friday 24th July

Activities:

- Define structured programme:

  - School offer

  - Outreach/in-school

  - Family workshops

  - Scope learning resources:

  - Classroom packs

  - Digital tools

Deliverables:

- Educational Programme Framework

- Resource Plan

- Engagement Strategy

Phase 4: Sustainability & Planning

Weeks 7 & 8 – Monday 27th July to Friday 7th August

Activities:

- Develop:

  - Income Vs Access Model

  - Pricing Approach

- Define:

  - Staffing Model

  - Educational Facilitator Role

  - Cost Programme Delivery

Deliverables:

- Costed Programme Plan

- Staffing & Workforce Model

- Volunteer training programme syllabus or resource list

- Income & Access Strategy

- Final Scoping Report (NLHF-ready)

Overall Project Deliverables

At the end of 8 weeks, the museum will have:

- A fully defined educational programme structure

- Tested and realistic delivery models

- Evidence-based audience insights

- Defined learning resource plans

- A balanced income and access model

- A clear staffing model (including Education Facilitator role)

- A costed and deliverable programme plan

- A final report ready to support NLHF application

Consultant Days

12 days total

| Week | Input |
| --- | --- |
| Week 1 & 2 | 3 days |
| Week 3 & 4 | 3 days |
| Week 5 & 6 | 3 days |
| Week 7 & 8 | 3 days |

Budget

| Freelance Consultant (12 Days) | £4200.00 (£350 per day) |
| --- | --- |
| Project Administration (3 hours per day, 12 days) | £486.00 (£13.50 per hour) |
| Total | £4686.00 |

Project Delivery

- Pre-Project Preparation (Funding & Planning)

- Submit application to Museum Development North Open Grants programme

- Develop outline project timeline and confirm key milestones

- Prepare draft brief and job description for freelance education specialist

- Identify key stakeholders (schools, partners, volunteers) for consultation

Considerations / Risks:

  - Funding not secured - Have a scaled-back internal review option or alternative funding routes

  - Delays in decision timelines - Build flexibility into project start dates

- Procurement of Freelance Specialist

- Advertise opportunity through relevant sector networks (e.g. GEM, Museum Development networks)

- Allow 2–3 weeks for recruitment, shortlisting, and interviews

- Select candidate with experience in museum learning, audience development, and programme design

- Agree contract, scope of work, and schedule of freelance days (12 days total)

Considerations / Risks:

- Limited applicant pool - Circulate widely and allow sufficient lead-in time

- Mismatch in expectations - Provide a clear brief and defined deliverables

- Project Management & Internal Capacity

- Museum Manager to provide approx. 3 hours per fortnight for:

  - Project coordination

  - Liaison with freelancer

  - Supporting consultation and testing

  - Ensure regular check-ins (e.g. weekly or bi-weekly)

  - Allocate time for internal review of outputs at each phase

Considerations / Risks:

  - Limited staff capacity: Keep scope tightly defined and schedule work in advance

  - Volunteer availability: Plan engagement early and communicate expectations clearly

- Delivery Phase (8 Weeks)

- Agree a clear timetable for freelance days across the 8 weeks (e.g. 1–2 days per week in blocks)

- Prioritise delivery during weekdays to align with:

  - School engagement

  - Staff availability

  - Avoid peak holiday periods where possible

- Research & Consultation Requirements

- Secure participation from:

  - At least one school group for testing workshop delivery

  - Local teachers and education partners for feedback

- Schedule consultation sessions (online where possible to reduce time/resource burden)

- Engage volunteers in structured feedback and testing activity

Considerations / Risks:

- Difficulty securing school engagement - Use existing relationships and offer flexible timing

- Low response to consultation - Keep sessions short, targeted, and easy to access

- Testing & Evaluation

- Deliver and observe at least one adapted workshop session

- Gather structured feedback from:

- Pupils

- Teachers

- Volunteers

- Ensure simple, consistent evaluation methods are used

Considerations / Risks:

- Limited testing opportunities - Focus on quality of feedback rather than quantity

- Inconsistent feedback - Use simple templates or guided questions

- Outputs & Review

- Schedule time at the end of each phase to review

- Findings

- Draft frameworks

- Recommendations

- Ensure final outputs are:

- Clear

- Costed

- Realistic within museum capacity

- Align outputs with requirements for future National Lottery Heritage Fund application

- Viability & Realistic Delivery

- Keep project scope focused on achievable outcomes within 12 freelance days

- Prioritise:

- Practical delivery models

- Sustainable staffing approaches

- Scalable programme design

- Ensure recommendations reflect:

- Current staffing (1 staff member + volunteers)

- Available space and resources

- Build in flexibility to adapt if challenges arise

Key Success Factors

- Clear project brief and defined outcomes

- Strong communication between museum and freelancer

- Early engagement with schools and stakeholders

- Realistic expectations of what can be achieved within timeframe

- Focus on practical, deliverable outputs

Overall

This project is viable and achievable within the proposed timeframe and resources, provided that planning, scheduling, and stakeholder engagement are carefully managed. By taking a structured and realistic approach, the museum can ensure the project delivers meaningful outcomes that directly support future funding and programme development.